## RTM
Requirement ID | Category | Requirement Description | Source | Priority | Design Specification | Development Status | Test Case ID | Test Status | Comments
BR-01 | Business | Reduce Global Food Waste: Combat food waste by creating a centralized platform that redistributes surplus food from businesses and individuals to those in need. | Project Charter – Purpose | High | Design Spec A | Not Started | TC-BR-01 | Not Tested | Core mission driver for the project; underpins all other requirements.
BR-02 | Business | Food Redistribution Target: Redistribute at least 1,000,000 pounds of surplus food within the first year of operation. | Project Charter – Objectives | High | Design Spec B | Not Started | TC-BR-02 | Not Tested | Key success metric reported via Impact Tracking Dashboard (FR-05).
BR-03 | Business | Environmental Impact Target: Save at least 2,000 tons of CO2-equivalent emissions in the first year of operation. | Project Charter – Objectives | High | Design Spec C | In Progress | TC-BR-03 | Not Tested | Tracked via impact tools; depends on FR-05 and FR-07 (carbon calculator integration).
BR-04 | Business | Global Expansion Target: Launch the platform in at least 10 major cities across three continents within 18 months. | Project Charter – Objectives | Medium | Design Spec D | In Progress | TC-BR-04 | Not Tested | Tied to TR-04 (localized city rollout packages).
SR-01 | Stakeholder | Donor Food Listing: Food donors (restaurants, grocery stores, producers) need a simple way to list surplus food with type, quantity, and expiration date. | Project Charter; PRD | High | Design Spec E | Not Started | TC-SR-01 | Not Tested | Directly implemented by FR-03.
SR-02 | Stakeholder | Regulatory Compliance Assurance: Regulatory bodies (EU Food Safety, US FDA) require the platform to comply with food safety and data privacy regulations (GDPR, CCPA). | Project Charter; Meeting Transcript 1 (Sept 28) | High | Design Spec F | Not Started | TC-SR-02 | Not Tested | See NFR-04; legal consultation ongoing per Charter risk mitigation.
FR-01 | Functional | User-Friendly Interface: Provide an intuitive, easy-to-navigate interface for both web and mobile applications across all user types. | Project Charter; PRD | High | Design Spec G | In Progress | TC-FR-01 | Not Tested | Foundational UX requirement; validated via usability testing.
FR-02 | Functional | Registration & Profile Management: Provide secure registration and profile management for all user categories, with a verification process for businesses and non-profits. | Project Charter; PRD | High | Design Spec H | Done | TC-FR-02 | In Progress | Implements SR-03.
FR-03 | Functional | Food Listing & Matching System: Allow donors to list surplus food (type, quantity, expiration date); allow recipients to search, claim, or request food by availability and proximity. | Project Charter; PRD | High | Design Spec I | Done | TC-FR-03 | In Progress | Core platform feature; implements SR-01 and SR-02.
FR-04 | Functional | Real-Time Notifications: Alert users about new listings, matches, pickup arrangements, and status updates. | Project Charter; PRD | High | Design Spec J | Not Started | TC-FR-04 | Not Tested | Depends on FR-03 event triggers.
FR-05 | Functional | Impact Tracking & Reporting: Log key metrics (meals donated, food waste reduced, carbon emissions saved) and allow users to generate/download reports. | Project Charter; PRD | High | Design Spec K | Not Started | TC-FR-05 | Not Tested | Feeds BR-02 and BR-03 reporting; Impact Tracking Dashboard deliverable.
FR-06 | Functional | Multilingual Support: Support multiple languages, initially English, Spanish, French, and Mandarin, with room to expand. | Project Charter; PRD | Medium | Design Spec L | Done | TC-FR-06 | Not Tested | Needed ahead of Global Expansion Target (BR-05).
FR-07 | Functional | Third-Party Service Integration: Integrate with mapping tools, carbon footprint calculators, and social media for sharing impact stories. | Project Charter; PRD; Meeting Transcript 2 (Sept 21) | High | Design Spec M | Not Started | TC-FR-07 | Not Tested | Highest technical risk area per Meeting 2 (API limitations, integration delays).
FR-08 | Functional | User Support Features: Provide FAQs, chat support, and educational content/resources within the platform. | Project Charter; PRD | Medium | Design Spec N | Not Started | TC-FR-08 | Not Tested | Part of User Support and Training Materials deliverable.
FR-09 | Functional | Interactive Onboarding Tutorials: Guide new users through key processes using pop-up tutorials or a chatbot to reduce onboarding friction. | PRD; Meeting Transcript 3 (Sept 14) | Medium | Design Spec O | Not Started | TC-FR-09 | Not Tested | Mitigation for low user-adoption risk; owner: Sofia Chen.
FR-10 | Functional | Simplified Sign-Up Process: Require minimal initial information so new users can register and start quickly. | PRD; Meeting Transcript 3 (Sept 14) | Medium | Design Spec P | Done | TC-FR-10 | In Progress | Mitigation for low user-adoption risk.
NFR-01 | Non-Functional | Scalability & Performance: Handle a growing number of users and transactions without compromising performance or user experience. | Project Charter; PRD | High | Design Spec Q | Not Started | TC-NFR-01 | Not Tested | Validated via load testing (QR-04).
NFR-02 | Non-Functional | Data Security & Privacy: Encrypt data at rest and in transit, use secure login protocols, and comply with GDPR, CCPA, and other data privacy regulations. | Project Charter; Meeting Transcript 1 (Sept 28) | High | Design Spec R | In Progress | TC-NFR-02 | Not Tested | Action owner: Sarah Johnson; implements SR-04/SR-05.
NFR-04 | Non-Functional | Multi-Factor Authentication: Require MFA for all access points, including internal users and API access. | Meeting Transcript 1 (Sept 28) | High | Design Spec T | Not Started | TC-NFR-04 | Not Tested | Action owner: Leo Tanaka (Cloud Services) – committed Sept 28.
QR-01 | Quality | QA Review Cycles: Conduct regular quality assurance reviews and testing phases to confirm the platform meets defined standards before release. | Project Charter – Governance | High | Design Spec U | Not Started | TC-QR-01 | Not Tested | Owned by Development Team QA process.
QR-02 | Quality | User Acceptance Testing: Complete formal UAT during the Testing & QA phase prior to pilot and full launch. | Project Charter – Schedule | High | Design Spec V | Not Started | TC-QR-02 | Not Tested | Scheduled for Months 8–9 per Charter timeline.
QR-03 | Quality | Continuous Feedback Loops: Collect user feedback continuously and feed actionable insights back into development. | Project Charter – Governance | Medium | Design Spec W | In Progress | TC-QR-03 | Not Tested | Supports BR-06 satisfaction target.
PJR-01 | Project | 12-Month Delivery Timeline: Complete full platform development and launch within 12 months of project initiation. | Project Charter – Objectives | High | Design Spec X | Not Started | TC-PJR-01 | Not Tested | Full Platform Launch scheduled Month 11 per Charter timeline.
PJR-02 | Project | Budget Adherence: Operate within the $1,700,000 total budget, including the contingency reserve. | Project Charter – Budget | High | Design Spec Y | Not Started | TC-PJR-02 | Not Tested | Tracked bi-weekly by PMO Financial Analysts.
PJR-03 | Project | Regulatory Compliance Constraint: Comply with applicable food safety regulations and data privacy laws (GDPR, CCPA) across all operating regions. | Project Charter – Constraints | High | Design Spec Z | Not Started | TC-PJR-03 | Not Tested | See SR-04, NFR-04, NFR-09.

## Legend & Notes
Requirements Traceability Matrix – Legend & Notes
Project: | Global Food Waste Reduction Network
Prepared: | July 2, 2026
Sources reviewed: | 01. Project Charter; 02. Project Research Areas; 03. Project Requirements Document; 04–06. Requirements Team Meeting Transcripts (Sept 14, 21, 28)
Requirement ID prefixes:
BR | Business Requirement
SR | Stakeholder Requirement
FR | Functional Requirement (Solution)
NFR | Non-Functional Requirement (Solution)
QR | Quality Requirement
TR | Transition Requirement
PJR | Project Requirement
Priority scale: | High = critical to launch / regulatory or safety-related; Medium = important but not launch-blocking; Low = enhances outcomes, lowest urgency
Status note: | Updated July 2, 2026: Development Status and Test Status now vary by requirement. Development Status: 16 Not Started, 5 In Progress, 4 Done. Test Status: 22 Not Tested, 3 In Progress (FR-02, FR-03, FR-10 — testing began after their development was marked Done), 0 Passed. Design Specification values remain placeholder labels (“Design Spec A…Z”) pending real document links. Keep this RTM, the Test Cases tab, and the dashboard in sync as statuses change.
Maintenance: | This RTM should be updated at each project gate (Design complete, Development sprints, UAT, Pilot Launch, Full Launch) to reflect current Design Specification references, Development Status, and Test Status.

## Test Cases
Test Case ID | Requirement ID | Test Scenario | Preconditions | Test Steps | Expected Result | Priority | Test Status | Comments
TC-BR-01 | BR-01 | Verify platform enables end-to-end surplus food redistribution | Registered and verified donor and recipient accounts exist. | 1. Donor lists a surplus food item. 2. Recipient searches and claims the item. 3. Confirm both parties receive confirmation. | The item moves from Listed to Claimed/Redistributed status and the transaction is recorded as a completed redistribution event. | High | Not Tested
TC-BR-02 | BR-02 | Verify Impact Dashboard aggregates total pounds of food redistributed | Multiple completed transactions exist with recorded food weights. | 1. Complete several list-and-claim cycles with known weights. 2. Open the Impact Tracking Dashboard. 3. Compare the dashboard total to the sum of individual transactions. | Dashboard displays the correct cumulative pounds redistributed, matching the sum of underlying transactions. | High | Not Tested
TC-BR-03 | BR-03 | Verify CO2-equivalent emissions saved is calculated and displayed accurately | Carbon footprint calculator integration (FR-07) is active; completed transactions exist. | 1. Complete a redistribution transaction with a known food type/weight. 2. Trigger the carbon calculator. 3. View the resulting value on the Impact Dashboard. | CO2e savings shown match the value computed by the carbon footprint calculator for the transaction(s). | High | Not Tested
TC-BR-04 | BR-04 | Verify platform supports city-specific configuration for new market launches | Admin access to city/region configuration. | 1. Add a new city profile (localized language, regional partners). 2. Enable the city for user registration. 3. Confirm users can register and see localized content. | New city is available for donor/recipient registration with correctly localized settings, supporting the 10-city expansion goal. | Medium | Not Tested
TC-SR-01 | SR-01 | Verify donor can list surplus food with required details | Donor is registered and verified. | 1. Log in as donor. 2. Navigate to List Food. 3. Enter food type, quantity, and expiration date. 4. Submit listing. | Listing is created and visible to eligible recipients, with all entered details displayed accurately. | High | Not Tested
TC-SR-02 | SR-02 | Verify platform enforces food-safety and data-privacy compliance at registration/listing | Compliance rule set configured (food-safety categories, GDPR/CCPA consent flow). | 1. Attempt to register without required consent/compliance information. 2. Attempt to submit a listing missing required food-safety fields. 3. Observe system response. | System blocks registration/listing submission until required compliance information is provided, and logs the compliance check. | High | Not Tested
TC-FR-01 | FR-01 | Verify a new user can complete core tasks without external help | Fresh, unauthenticated user; usability test script defined. | 1. Open platform on web and mobile. 2. Attempt to register, list food, and search for food without guidance. 3. Record time-to-completion and errors encountered. | User completes core tasks within the target time/error thresholds defined by the usability test plan. | High | Not Tested
TC-FR-02 | FR-02 | Verify secure registration and profile management with verification for business/non-profit users | None. | 1. Register as a business user with required business details. 2. Submit for verification. 3. Attempt to edit profile after verification. | Business account is not fully activated until verification is complete; profile edits are saved securely and require re-authentication for sensitive changes. | High | In Progress
TC-FR-03 | FR-03 | Verify recipient can search and claim food based on proximity | Active food listings exist in multiple locations. | 1. Recipient searches for available food. 2. Filter results by proximity. 3. Claim a nearby listing. | Results are filtered correctly by proximity; claiming reserves the item for that recipient and removes it from other recipients' search results. | High | In Progress
TC-FR-04 | FR-04 | Verify users receive a real-time notification when a listing is claimed | Donor has an active listing. | 1. Recipient claims the donor's listing. 2. Observe the donor's notification center in real time. | Donor receives a notification within an acceptable latency threshold (e.g., <30 seconds) including pickup details. | High | Not Tested
TC-FR-05 | FR-05 | Verify user can generate and download an impact report | User has completed transaction history. | 1. Navigate to Impact Tracking. 2. Select a date range. 3. Generate and download the report. | Report contains accurate metrics (meals donated, food waste reduced, CO2 saved) for the selected period, in the expected download format. | High | Not Tested
TC-FR-06 | FR-06 | Verify platform displays correctly in each supported language | None. | 1. Change language setting to Spanish, then French, then Mandarin. 2. Navigate through registration, listing, and search screens. | All UI text and system messages are correctly translated and rendered with no missing strings or layout issues. | Medium | Not Tested
TC-FR-07 | FR-07 | Verify mapping tool correctly displays nearby listings | Mapping API integration configured; listings have valid location data. | 1. Recipient opens map view. 2. Observe markers for nearby food listings. 3. Select a marker to view listing details. | Map accurately displays listing locations; selecting a marker navigates to the correct listing detail. | High | Not Tested
TC-FR-08 | FR-08 | Verify user can access FAQs and initiate chat support | User is logged in. | 1. Navigate to Help/Support. 2. Search FAQ for a topic. 3. Initiate chat support if FAQ doesn't resolve the issue. | Relevant FAQ results are returned; chat support session connects to an agent or bot within the expected response time. | Medium | Not Tested
TC-FR-09 | FR-09 | Verify new users are guided through onboarding via tutorial/chatbot | First-time login. | 1. Log in for the first time. 2. Observe onboarding tutorial trigger. 3. Complete or skip tutorial steps. | Tutorial/chatbot appears automatically for first-time users guiding key actions, and does not reappear on subsequent logins. | Medium | Not Tested
TC-FR-10 | FR-10 | Verify sign-up requires only minimal required fields | None. | 1. Begin registration. 2. Enter only minimum required fields (name, email, password, user type). 3. Submit. | Registration completes successfully with minimal information; additional profile details can be added later without blocking account creation. | Medium | In Progress
TC-NFR-01 | NFR-01 | Verify platform maintains performance under peak concurrent user load | Load-testing environment configured per performance plan. | 1. Simulate peak concurrent user load. 2. Execute core transactions (search, list, claim) concurrently. 3. Measure response times and error rates. | Platform maintains acceptable response times and zero critical errors under target peak load, per performance benchmarks. | High | Not Tested
TC-NFR-02 | NFR-02 | Verify sensitive data is encrypted at rest and in transit | Test data set including PII. | 1. Submit user PII through the registration form. 2. Inspect network traffic for TLS encryption. 3. Inspect database storage for encryption at rest. | All PII is transmitted over encrypted channels and stored encrypted at rest; no sensitive data is exposed in plaintext. | High | Not Tested
TC-NFR-04 | NFR-04 | Verify MFA is enforced on login for all user types and API access | User account with MFA enabled. | 1. Attempt login with correct username/password only. 2. Confirm MFA challenge is presented. 3. Complete MFA challenge (e.g., OTP). 4. Attempt an API call without a valid MFA-derived token. | Login is not completed until the MFA challenge is satisfied; API access without a valid authentication token is rejected. | High | Not Tested
TC-QR-01 | QR-01 | Verify each release candidate passes the QA review checklist before deployment | A release candidate build is available. | 1. Execute the QA checklist against the release candidate (functional, security, performance spot-checks). 2. Log any defects found. 3. Confirm the sign-off gate blocks deployment until the checklist passes. | Release candidate cannot be promoted to production until all QA checklist items pass or are explicitly waived by the QA lead. | High | Not Tested
TC-QR-02 | QR-02 | Verify UAT participants can complete acceptance scenarios and formally sign off | UAT environment available with representative data; participants identified. | 1. UAT participants execute assigned acceptance test scripts. 2. Record pass/fail results. 3. Collect formal sign-off from business stakeholders. | All critical acceptance scenarios pass, and formal UAT sign-off is documented before pilot launch approval. | High | Not Tested
TC-QR-03 | QR-03 | Verify in-app feedback is captured and routed to the development backlog | Feedback mechanism is available in the platform. | 1. Submit feedback via the in-app feedback form. 2. Confirm feedback is logged in the feedback/backlog system. 3. Verify a team member can view and triage the feedback. | Feedback is reliably captured with relevant metadata (user, timestamp, context) and visible to the product team for triage. | Medium | Not Tested
TC-PJR-01 | PJR-01 | Verify milestone tracking flags schedule slippage against the 12-month plan | Project schedule baseline loaded into PM tool per Charter timeline. | 1. Update task completion status in the project schedule. 2. Compare actual progress to baseline at a checkpoint. 3. Review status report to PMO. | Schedule tracking accurately reflects variance from the 12-month baseline and is reported to the Executive Steering Committee per governance cadence. | High | Not Tested
TC-PJR-02 | PJR-02 | Verify budget tracking reflects actual spend against budget and contingency | Budget baseline loaded into financial tracking tool. | 1. Record actual expenditures across categories. 2. Compare actual vs. budgeted amounts. 3. Verify contingency reserve usage is tracked separately. | Budget report accurately reflects spend-to-date, remaining budget, and contingency utilization, with variances flagged for PMO review. | High | Not Tested
TC-PJR-03 | PJR-03 | Verify platform operations remain compliant with regional regulations | Region-specific compliance rules configured. | 1. Register users from an EU region and a US (CCPA-applicable) region. 2. Verify region-appropriate consent flows and data handling. 3. Review the compliance audit log. | Platform applies region-appropriate compliance rules automatically, and an auditable compliance log is available for regulatory review. | High | Not Tested

## Traceability Verification
Test Case ↔ RTM Traceability Verification
Verification date: | July 2, 2026 (updated)
Total RTM requirement rows: | 25
Total test cases authored: | 25
Coverage: | 1 test case written for every row currently in the RTM sheet (100% coverage).
Test Case ID corrections made (prior pass)
The RTM's Test Case ID column previously contained IDs left over from before rows were deleted during the team's requirements review. These were corrected to the TC-<Requirement ID> pattern so every ID in the RTM matches exactly one test case on the Test Cases tab:
RTM Row (at the time) | Requirement ID | Old Test Case ID | Corrected Test Case ID
5 | BR-04 | TC-BR-05 | TC-BR-04
7 | SR-02 | TC-SR-04 | TC-SR-02
19 | NFR-02 | TC-NFR-04 | TC-NFR-02
20 | NFR-03 | TC-NFR-04 | TC-NFR-03
21 | NFR-04 | TC-NFR-05 | TC-NFR-04
Resolved issue | Previously, rows NFR-02 and NFR-03 contained identical requirement text (“Data security & privacy…”), making TC-NFR-02 and TC-NFR-03 duplicate test cases. The team removed row NFR-03 (and its test case TC-NFR-03) from the workbook, consolidating the requirement into NFR-02. The RTM and Test Cases tabs now contain 25 rows each with no duplicates.
Status sync | The Test Cases tab's Test Status column is now synced with the RTM: FR-02, FR-03, and FR-10 show Test Status = In Progress (matching their RTM row), reflecting that development is Done and testing has begun for those three requirements. All other rows remain Not Tested, consistent with their current Development Status.
Result: | Every requirement in the RTM has exactly one correctly-linked, non-duplicate test case, and Test Status values are consistent between the RTM and Test Cases tabs.